## Sheet1
Topic | Description/Feedback | Team Comments | MJB Comments
General | In the opening screen would the app recognize the user logged onto the device? Good to know who is using and making comments. | Do we need to introduce login management system? What are the requirements? | Yes. Let's add a login system. If a full login system is going to take more than a couple days, then just create a fake login. Use the username for comments.
| Will the shopping cart and search icons display on every page? Drawing pages do not show them. | Yes, we could bring both search and cart icon on all the pages. | Please do.
| The header of the web page appears to overlay the upper portion of the Plant Map drawing | We have displayed the actual image provided by the client. The upper portion was already missing in the supplied image | OK. I'll let Scott know
| In the plan map View References (characters inside a circle) may be overlaid by the rectangular equipment hotspots. We probably don’t need to account for it here. In the future we may want a drop down that allows selection of views referenced from the visible drawing. Note: These views can be on the same drawing or on another drawing. The alternative way of making the hotspots would be to capture the text as a hotspot. It would be rare you would see text overlaying text. Thus, all text would be “clickable” We’ll need to get a read from them on what they want to do. For scanned drawings such as the plant map, there may be extra burden to make the text real for hotspotting purposes. | We need more clarification and actual requirement. Please explain. | I'll clarify with Scott
2500 Ton Hydraulic press 2583 Page
| Shopping Card but no search | We could add the search icon here. | Please do.
| I just noticed, is it possible to capture a “bread-crumb” trail or log of how I got to where I am and decide if I want to go back to something specific. Example: Adobe Lightroom has a history dialog showing every action I’ve taken and permits me to navigate to any point in that history if I choose. This is useful to help you get back to a common point when doing diagnostics. It’s also good when you have to explain how you found the problem to your boss. | Yes, we could add the "bread-crumb" trail. Is it Ok if we add hardcoded "bread-cumbs" for now? | Please do. Hardcoded is fine.
2500 Ton Hydraulic Press Hydraulic Drawing
| Will there be bi-directional linking from the part numbers in parts table to the callouts in the drawing? | Yes, we could, but need more information on which part should be linked to which diagram or vice versa. Using that information, we could build a map to support bi-directional linking | I'll get more information.
| Will there be the ability to click on the part in the table or drawing and insert it into the shopping cart? | Yes, we could, but need more information. | I'll get more information.
| On a tablet, would a long press also add to the shopping cart. | Yes, we could, but need more information. | I'll get more information.
| Within the shopping cart is it possible to navigate back to the drawing/hotspot origin | Currently not supported. Yes, we could implement but need more information. | I'll get more information.
2500 Ton Hydraulic Press Electrical Diagram
| Text and some details are missing on the drawing. | We have displayed the actual image provided by the client. | I'll clarify with Scott
| This drawing origin is Vector. Is there a way to display vector drawings as SVG? | Most of the browsers supports SVG. We need the sample files for further analysis. | I'll clarify with Scott
| Attached are a few screenshots captured from the Autodesk free viewer as PDF files. No choice to save them to SVG with this tool. There is something in the .DWG file that causes IsoDraw to crash. Otherwise I could use IsoDraw for file processing. | We have not received the screenshots. | I'll clarify with Scott
| There is an upward arrow in the lower right of the screen. What’s that for? | Arrow is used to navigate to the top of the page when there are large diagrams. This has been fixed now. | Great thanks.
Subsystems Vane Pump
| No Navigation buttons on this page | We'll add the bread-crumbs on this page for easier navigation. | Great thanks.
| Using iPad and pressing link displays only a distorted image. PDF is not displayed | Not sure if you're using Chrome browser in your iPad. We have used the native chrome PDF viewer support to display the PDF. Please try using Chrome browser and let us know. | I'll clarify with Scott
| Were we going to discuss a method of capturing comments/feedback on 3rd party documents? | We could discuss on this during the call. | I'll clarify with Scott